# POU (Plan of Upgrade) - Huawei WLAN  Upgrade

## 1. Executive Summary

Upgrade Huawei AC6508 controller and  AP5760-51 access points to address end-of-support risks, security vulnerabilities, and performance issues. Total estimated time: 6 hours during maintenance window.

## 2. Current vs Target Versions

| Component | Current Version | Target Version |
| --- | --- | --- |
| AC 6508 | V200R021C00SPC100 | V200R024C00SPC100 |
| AP 5760-51 | V200R019C10SPC300 | V200R024C10SPC100 |

## 3. Business Drivers

- Security Risk: Current versions have unpatched vulnerabilities

- No Vendor Support: End of technical support

- Performance Issues: Poor connectivity in banking halls

- Compliance: Needed for PCI-DSS and banking regulations

## 4. Scope

- ✅ Upgrade 2x AC6508 controller

- ✅ Upgrade 24x AP5760-51 access points

- ✅ Rename APs with location-based naming

- ❌ No changes to network cabling

- ❌ No changes to core switches

## 5. Risk Assessment

| Risk | Impact | Mitigation |
| --- | --- | --- |
| AC upgrade failure | High | Console access ready, backup firmware |
| APs not coming online | Medium | Batch upgrade, rollback plan |
| Business disruption | Medium | Weekend maintenance, communication |

## 6. Success Criteria

- All APs online with new firmware

- All VLANs (8-10,12-16,99,102) accessible

- Performance improved by 30%

Approval Required:

- Maintenance Window: [Date], [Time]

- Team: [Prashant Khadgi, Biyudh Lama]

Submitted by: Biyudh Lama
Approved by: ___________________

# POA (Plan of Action) - Huawei WLAN Upgrade

## Phase 1: Pre-Maintenance Preparation

Time: Before maintenance day
Tasks:

- Confirm firmware compatibility with Huawei

- Download V200R024C00SPC100 (AC) and V200R024C10SPC100 (AP)

- Notify all respective person of maintenance

- Prepare SSH with legacy algorithms support

## Phase 2: Maintenance Execution (6 Hours)

### Phase 2.1: Backup & Preparation (80 min)

| Task | Duration |  |
| --- | --- | --- |
| 1. Rename APs (location-wise) | 20 min |  |
| 2. Backup AC configuration | 30 min |  |
| 3. Backup all switches | 30 min |  |

### Phase 2.2: AC Upgrade (30 min)

- Upload AC firmware to controller

- Set as startup: startup system-software V200R024C00SPC100.cc

- Save and reboot

- Verify new version: display version

### Phase 2.3: All AP Upgrade  push (2 hours)

- Upload AP firmware to AC

- Upgrade in batches

### Phase 2.4: Apply Patches (1 hour)

- Apply any required post-upgrade patches

- Verify no compatibility issues

### Phase 2.5: Testing (1 hour)

- Test all VLANs (8-10,12-16,99,102)

- Performance test

- Management access test

### Phase 2.6: Finalize (10 min)

- Update documentation

- Send completion notification

- Schedule next-day follow-up

## Phase 3: Post-Maintenance

Time: Next business day

- Monitor network for 24 hours

- Gather user feedback

- Update monitoring systems

- Project documentation closure

## Rollback Plan

Trigger: >30% APs offline for >1 hour
Action:

- Restore AC from backup firmware

- Revert APs using old .pat files

- Restore configurations

- Reschedule upgrade

## Communication Plan

- Pre-maintenance: Email to Responsible person

- During maintenance: communication at each phase start

- Post-maintenance: Completion email with support contact

## Dishhome Team & Contacts

- Project Lead: Binda Bilami

- Technical Lead: Prashant Khadgi, Biyudh Lama

- Management Escalation: Dishhome Enterprise support 01-5970977

Submitted by: Biyudh Lama
Approved by: ___________________